## Welcome
ISO 27001 Project Plan
This template provides guidance on how to implement an ISMS according to ISO/IEC 27001. By purchasing this file, you agree to keep its contents confidential and not to share, distribute, or disclose it to any third parties without the express written permission of Aron Lange. Any unauthorized distribution or disclosure of this file may lead to legal action against you. The information contained in this file is for general information purposes only. The information is provided by Aron Lange and while we endeavor to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability or availability with respect to the file or the information, products, services, or related graphics contained in the file for any purpose. Any reliance you place on such information is therefore strictly at your own risk. In no event will we be liable for any loss or damage including without limitation, indirect or consequential loss or damage, or any loss or damage whatsoever arising from loss of data or profits arising out of, or in connection with, the use of this file.
Publisher: Aron Lange © 2025 Aron Lange, Germany https://grclab.com

## Normative References
Normative references
Row Labels
4 Context of the organization
4.1 Understanding the organization and its context
4.2 Understanding the needs and expectations of interested parties
4.3 Determining the scope of the information security management system
4.4 Information security management system
5 Leadership
5.1 Leadership and commitment
5.2 Policy
5.3 Organizational roles, responsibilities and authorities
6 Planning
6.1 Actions to address risks and opportunities
6.2 Information security objectives and planning to achieve them
6.3 Planning of changes
7 Support
7.1 Resources
7.2 Competence
7.3 Awareness
7.4 Communication
7.5 Documented information
8 Operations
8.1 Operational planning and control
8.2 Information security risk assessment
8.3 Information security risk treatment
9 Performance evaluation
9.1 Monitoring, measurement, analysis and evaluation
9.2 Internal audit
9.3 Management review
10 Improvement
10.1 Continual improvement
10.2 Nonconformity and corrective action
Annex A
5 Organizational controls
6 People controls
7 Physical controls
8 Technological controls
Grand Total

## Citations
Reference | Type | Clause | Subclause | Description
4.1 ¶1 | Core Topic | 4 Context of the organization | 4.1 Understanding the organization and its context | Due to copyright protection, this resource can not provide you with the actual citations of ISO/IEC 27001:2022. However you can add the text from your personal licensed copy.
4.2 a) | Core Topic | 4 Context of the organization | 4.2 Understanding the needs and expectations of interested parties
4.2 b) | Core Topic | 4 Context of the organization | 4.2 Understanding the needs and expectations of interested parties
4.2 c) | Core Topic | 4 Context of the organization | 4.2 Understanding the needs and expectations of interested parties
4.3 ¶1 | Core Topic | 4 Context of the organization | 4.3 Determining the scope of the information security management system
4.3 a) | Core Topic | 4 Context of the organization | 4.3 Determining the scope of the information security management system
4.3 b) | Core Topic | 4 Context of the organization | 4.3 Determining the scope of the information security management system
4.3 c) | Core Topic | 4 Context of the organization | 4.3 Determining the scope of the information security management system
4.3 ¶2 | Core Topic | 4 Context of the organization | 4.3 Determining the scope of the information security management system
4.4 ¶1 | Core Topic | 4 Context of the organization | 4.4 Information security management system
5.1 a) | Core Topic | 5 Leadership | 5.1 Leadership and commitment
5.1 b) | Core Topic | 5 Leadership | 5.1 Leadership and commitment
5.1 c) | Core Topic | 5 Leadership | 5.1 Leadership and commitment
5.1 d) | Core Topic | 5 Leadership | 5.1 Leadership and commitment
5.1 e) | Core Topic | 5 Leadership | 5.1 Leadership and commitment
5.1 f) | Core Topic | 5 Leadership | 5.1 Leadership and commitment
5.1 g) | Core Topic | 5 Leadership | 5.1 Leadership and commitment
5.1 h) | Core Topic | 5 Leadership | 5.1 Leadership and commitment
5.2 a) | Core Topic | 5 Leadership | 5.2 Policy
5.2 b) | Core Topic | 5 Leadership | 5.2 Policy
5.2 c) | Core Topic | 5 Leadership | 5.2 Policy
5.2 d) | Core Topic | 5 Leadership | 5.2 Policy
5.2 e) | Core Topic | 5 Leadership | 5.2 Policy
5.2 f) | Core Topic | 5 Leadership | 5.2 Policy
5.2 g) | Core Topic | 5 Leadership | 5.2 Policy
5.3 ¶1 | Core Topic | 5 Leadership | 5.3 Organizational roles, responsibilities and authorities
5.3 a) | Core Topic | 5 Leadership | 5.3 Organizational roles, responsibilities and authorities
5.3 b) | Core Topic | 5 Leadership | 5.3 Organizational roles, responsibilities and authorities
6.1.1 a) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.1 b) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.1 c) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.1 d) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.1 e) 1) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.1 e) 2) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.2 a) 1) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.2 a) 2) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.2 b) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.2 c) 1) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.2 c) 2) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.2 d) 1) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.2 d) 2) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.2 d) 3) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.2 e) 1) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.2 e) 2) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.2 ¶1 | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.3 a) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.3 b) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.3 c) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.3 d) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.3 e) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.3 f) | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.1.3 ¶1 | Core Topic | 6 Planning | 6.1 Actions to address risks and opportunities
6.2 ¶1 | Core Topic | 6 Planning | 6.2 Information security objectives and planning to achieve them
6.2 a) | Core Topic | 6 Planning | 6.2 Information security objectives and planning to achieve them
6.2 b) | Core Topic | 6 Planning | 6.2 Information security objectives and planning to achieve them
6.2 c) | Core Topic | 6 Planning | 6.2 Information security objectives and planning to achieve them
6.2 d) | Core Topic | 6 Planning | 6.2 Information security objectives and planning to achieve them
6.2 e) | Core Topic | 6 Planning | 6.2 Information security objectives and planning to achieve them
6.2 f) | Core Topic | 6 Planning | 6.2 Information security objectives and planning to achieve them
6.2 g) | Core Topic | 6 Planning | 6.2 Information security objectives and planning to achieve them
6.2 ¶2 | Core Topic | 6 Planning | 6.2 Information security objectives and planning to achieve them
6.2 h) | Core Topic | 6 Planning | 6.2 Information security objectives and planning to achieve them
6.2 i) | Core Topic | 6 Planning | 6.2 Information security objectives and planning to achieve them
6.2 j) | Core Topic | 6 Planning | 6.2 Information security objectives and planning to achieve them
6.2 k) | Core Topic | 6 Planning | 6.2 Information security objectives and planning to achieve them
6.2 l) | Core Topic | 6 Planning | 6.2 Information security objectives and planning to achieve them
6.3 ¶1 | Core Topic | 6 Planning | 6.3 Planning of changes
7.1 ¶1 | Core Topic | 7 Support | 7.1 Resources
7.2 a) | Core Topic | 7 Support | 7.2 Competence
7.2 b) | Core Topic | 7 Support | 7.2 Competence
7.2 c) | Core Topic | 7 Support | 7.2 Competence
7.2 d) | Core Topic | 7 Support | 7.2 Competence
7.3 a) | Core Topic | 7 Support | 7.3 Awareness
7.3 b) | Core Topic | 7 Support | 7.3 Awareness
7.3 c) | Core Topic | 7 Support | 7.3 Awareness
7.4 a) | Core Topic | 7 Support | 7.4 Communication
7.4 b) | Core Topic | 7 Support | 7.4 Communication
7.4 c) | Core Topic | 7 Support | 7.4 Communication
7.4 d) | Core Topic | 7 Support | 7.4 Communication
7.5.1 a) | Core Topic | 7 Support | 7.5 Documented information
7.5.1 b) | Core Topic | 7 Support | 7.5 Documented information
7.5.2 a) | Core Topic | 7 Support | 7.5 Documented information
7.5.2 b) | Core Topic | 7 Support | 7.5 Documented information
7.5.2 c) | Core Topic | 7 Support | 7.5 Documented information
7.5.3 a) | Core Topic | 7 Support | 7.5 Documented information
7.5.3 b) | Core Topic | 7 Support | 7.5 Documented information
7.5.3 c) | Core Topic | 7 Support | 7.5 Documented information
7.5.3 d) | Core Topic | 7 Support | 7.5 Documented information
7.5.3 e) | Core Topic | 7 Support | 7.5 Documented information
7.5.3 f) | Core Topic | 7 Support | 7.5 Documented information
7.5.3 ¶1 | Core Topic | 7 Support | 7.5 Documented information
8.1 ¶1 | Core Topic | 8 Operations | 8.1 Operational planning and control
8.1 ¶2 | Core Topic | 8 Operations | 8.1 Operational planning and control
8.1 ¶3 | Core Topic | 8 Operations | 8.1 Operational planning and control
8.1 ¶4 | Core Topic | 8 Operations | 8.1 Operational planning and control
8.2 ¶1 | Core Topic | 8 Operations | 8.2 Information security risk assessment
8.2 ¶2 | Core Topic | 8 Operations | 8.2 Information security risk assessment
8.3 ¶1 | Core Topic | 8 Operations | 8.3 Information security risk treatment
8.3 ¶2 | Core Topic | 8 Operations | 8.3 Information security risk treatment
9.1 a) | Core Topic | 9 Performance evaluation | 9.1 Monitoring, measurement, analysis and evaluation
9.1 b) | Core Topic | 9 Performance evaluation | 9.1 Monitoring, measurement, analysis and evaluation
9.1 c) | Core Topic | 9 Performance evaluation | 9.1 Monitoring, measurement, analysis and evaluation
9.1 d) | Core Topic | 9 Performance evaluation | 9.1 Monitoring, measurement, analysis and evaluation
9.1 e) | Core Topic | 9 Performance evaluation | 9.1 Monitoring, measurement, analysis and evaluation
9.1 f) | Core Topic | 9 Performance evaluation | 9.1 Monitoring, measurement, analysis and evaluation
9.1 ¶1 | Core Topic | 9 Performance evaluation | 9.1 Monitoring, measurement, analysis and evaluation
9.1 ¶2 | Core Topic | 9 Performance evaluation | 9.1 Monitoring, measurement, analysis and evaluation
9.2.1 a) 1) | Core Topic | 9 Performance evaluation | 9.2 Internal audit
9.2.1 a) 2) | Core Topic | 9 Performance evaluation | 9.2 Internal audit
9.2.1 b) | Core Topic | 9 Performance evaluation | 9.2 Internal audit
9.2.2 ¶1 | Core Topic | 9 Performance evaluation | 9.2 Internal audit
9.2.2 ¶2 | Core Topic | 9 Performance evaluation | 9.2 Internal audit
9.2.2 a) | Core Topic | 9 Performance evaluation | 9.2 Internal audit
9.2.2 b) | Core Topic | 9 Performance evaluation | 9.2 Internal audit
9.2.2 c) | Core Topic | 9 Performance evaluation | 9.2 Internal audit
9.2.2 ¶3 | Core Topic | 9 Performance evaluation | 9.2 Internal audit
9.3.1 ¶1 | Core Topic | 9 Performance evaluation | 9.3 Management review
9.3.2 a) | Core Topic | 9 Performance evaluation | 9.3 Management review
9.3.2 b) | Core Topic | 9 Performance evaluation | 9.3 Management review
9.3.2 c) | Core Topic | 9 Performance evaluation | 9.3 Management review
9.3.2 d) 1) | Core Topic | 9 Performance evaluation | 9.3 Management review
9.3.2 d) 2) | Core Topic | 9 Performance evaluation | 9.3 Management review
9.3.2 d) 3) | Core Topic | 9 Performance evaluation | 9.3 Management review
9.3.2 d) 4) | Core Topic | 9 Performance evaluation | 9.3 Management review
9.3.2 e) | Core Topic | 9 Performance evaluation | 9.3 Management review
9.3.2 f) | Core Topic | 9 Performance evaluation | 9.3 Management review
9.3.2 g) | Core Topic | 9 Performance evaluation | 9.3 Management review
9.3.3 ¶1 | Core Topic | 9 Performance evaluation | 9.3 Management review
9.3.3 ¶2 | Core Topic | 9 Performance evaluation | 9.3 Management review
10.1 ¶1 | Core Topic | 10 Improvement | 10.1 Continual improvement
10.2 a) 1) | Core Topic | 10 Improvement | 10.2 Nonconformity and corrective action
10.2 a) 2) | Core Topic | 10 Improvement | 10.2 Nonconformity and corrective action
10.2 b) 1) | Core Topic | 10 Improvement | 10.2 Nonconformity and corrective action
10.2 b) 2) | Core Topic | 10 Improvement | 10.2 Nonconformity and corrective action
10.2 b) 3) | Core Topic | 10 Improvement | 10.2 Nonconformity and corrective action
10.2 c) | Core Topic | 10 Improvement | 10.2 Nonconformity and corrective action
10.2 d) | Core Topic | 10 Improvement | 10.2 Nonconformity and corrective action
10.2 e) | Core Topic | 10 Improvement | 10.2 Nonconformity and corrective action
10.2 ¶1 | Core Topic | 10 Improvement | 10.2 Nonconformity and corrective action
10.2 f) | Core Topic | 10 Improvement | 10.2 Nonconformity and corrective action
10.2 g) | Core Topic | 10 Improvement | 10.2 Nonconformity and corrective action
A.5.1 | Control | Annex A | 5 Organizational controls
A.5.2 | Control | Annex A | 5 Organizational controls
A.5.3 | Control | Annex A | 5 Organizational controls
A.5.4 | Control | Annex A | 5 Organizational controls
A.5.5 | Control | Annex A | 5 Organizational controls
A.5.6 | Control | Annex A | 5 Organizational controls
A.5.7 | Control | Annex A | 5 Organizational controls
A.5.8 | Control | Annex A | 5 Organizational controls
A.5.9 | Control | Annex A | 5 Organizational controls
A.5.10 | Control | Annex A | 5 Organizational controls
A.5.11 | Control | Annex A | 5 Organizational controls
A.5.12 | Control | Annex A | 5 Organizational controls
A.5.13 | Control | Annex A | 5 Organizational controls
A.5.14 | Control | Annex A | 5 Organizational controls
A.5.15 | Control | Annex A | 5 Organizational controls
A.5.16 | Control | Annex A | 5 Organizational controls
A.5.17 | Control | Annex A | 5 Organizational controls
A.5.18 | Control | Annex A | 5 Organizational controls
A.5.19 | Control | Annex A | 5 Organizational controls
A.5.20 | Control | Annex A | 5 Organizational controls
A.5.21 | Control | Annex A | 5 Organizational controls
A.5.22 | Control | Annex A | 5 Organizational controls
A.5.23 | Control | Annex A | 5 Organizational controls
A.5.24 | Control | Annex A | 5 Organizational controls
A.5.25 | Control | Annex A | 5 Organizational controls
A.5.26 | Control | Annex A | 5 Organizational controls
A.5.27 | Control | Annex A | 5 Organizational controls
A.5.28 | Control | Annex A | 5 Organizational controls
A.5.29 | Control | Annex A | 5 Organizational controls
A.5.30 | Control | Annex A | 5 Organizational controls
A.5.31 | Control | Annex A | 5 Organizational controls
A.5.32 | Control | Annex A | 5 Organizational controls
A.5.33 | Control | Annex A | 5 Organizational controls
A.5.34 | Control | Annex A | 5 Organizational controls
A.5.35 | Control | Annex A | 5 Organizational controls
A.5.36 | Control | Annex A | 5 Organizational controls
A.5.37 | Control | Annex A | 5 Organizational controls
A.6.1 | Control | Annex A | 6 People controls
A.6.2 | Control | Annex A | 6 People controls
A.6.3 | Control | Annex A | 6 People controls
A.6.4 | Control | Annex A | 6 People controls
A.6.5 | Control | Annex A | 6 People controls
A.6.6 | Control | Annex A | 6 People controls
A.6.7 | Control | Annex A | 6 People controls
A.6.8 | Control | Annex A | 6 People controls
A.7.1 | Control | Annex A | 7 Physical controls
A.7.2 | Control | Annex A | 7 Physical controls
A.7.3 | Control | Annex A | 7 Physical controls
A.7.4 | Control | Annex A | 7 Physical controls
A.7.5 | Control | Annex A | 7 Physical controls
A.7.6 | Control | Annex A | 7 Physical controls
A.7.7 | Control | Annex A | 7 Physical controls
A.7.8 | Control | Annex A | 7 Physical controls
A.7.9 | Control | Annex A | 7 Physical controls
A.7.10 | Control | Annex A | 7 Physical controls
A.7.11 | Control | Annex A | 7 Physical controls
A.7.12 | Control | Annex A | 7 Physical controls
A.7.13 | Control | Annex A | 7 Physical controls
A.7.14 | Control | Annex A | 7 Physical controls
A.8.1 | Control | Annex A | 8 Technological controls
A.8.2 | Control | Annex A | 8 Technological controls
A.8.3 | Control | Annex A | 8 Technological controls
A.8.4 | Control | Annex A | 8 Technological controls
A.8.5 | Control | Annex A | 8 Technological controls
A.8.6 | Control | Annex A | 8 Technological controls
A.8.7 | Control | Annex A | 8 Technological controls
A.8.8 | Control | Annex A | 8 Technological controls
A.8.9 | Control | Annex A | 8 Technological controls
A.8.10 | Control | Annex A | 8 Technological controls
A.8.11 | Control | Annex A | 8 Technological controls
A.8.12 | Control | Annex A | 8 Technological controls
A.8.13 | Control | Annex A | 8 Technological controls
A.8.14 | Control | Annex A | 8 Technological controls
A.8.15 | Control | Annex A | 8 Technological controls
A.8.16 | Control | Annex A | 8 Technological controls
A.8.17 | Control | Annex A | 8 Technological controls
A.8.18 | Control | Annex A | 8 Technological controls
A.8.19 | Control | Annex A | 8 Technological controls
A.8.20 | Control | Annex A | 8 Technological controls
A.8.21 | Control | Annex A | 8 Technological controls
A.8.22 | Control | Annex A | 8 Technological controls
A.8.23 | Control | Annex A | 8 Technological controls
A.8.24 | Control | Annex A | 8 Technological controls
A.8.25 | Control | Annex A | 8 Technological controls
A.8.26 | Control | Annex A | 8 Technological controls
A.8.27 | Control | Annex A | 8 Technological controls
A.8.28 | Control | Annex A | 8 Technological controls
A.8.29 | Control | Annex A | 8 Technological controls
A.8.30 | Control | Annex A | 8 Technological controls
A.8.31 | Control | Annex A | 8 Technological controls
A.8.32 | Control | Annex A | 8 Technological controls
A.8.33 | Control | Annex A | 8 Technological controls
A.8.34 | Control | Annex A | 8 Technological controls

## Deliverables
ID | Name | Category | Type | Citations
1 | Information security policy | Policy | Mandatory | 5.2 e),5.2 f),5.2 g),A.5.1
2 | Topic-specific policy on system development | Topic-specific policy | Additional | A.8.25,A.8.26,A.8.27,A.8.28,A.8.29,A.8.30
3 | Topic-specific policy on access control | Topic-specific policy | Additional | A.5.15
4 | Topic-specific policy on system security | Topic-specific policy | Additional | A.8.20,A.8.24
5 | Topic-specific policy on information security incident management | Topic-specific policy | Additional | A.5.24
6 | Topic-specific policy on business continuity | Topic-specific policy | Additional | A.5.29,A.8.13
7 | Topic-specific policy on risk management | Topic-specific policy | Additional
8 | Topic-specific policy on asset and configuration management | Topic-specific policy | Additional | A.5.9
9 | Topic-specific policy on information handling | Topic-specific policy | Additional | A.7.7,A.5.10,A.5.14
10 | Topic-specific policy on personnel security | Topic-specific policy | Additional | A.6.1
11 | Topic-specific policy on information classification | Topic-specific policy | Additional | A.5.12
12 | Topic-specific policy on identification and authentication | Topic-specific policy | Additional | A.5.17,A.5.16
13 | Topic-specific policy on supply chain risk management | Topic-specific policy | Additional | A.5.19,A.5.23
14 | Topic-specific policy on records management | Topic-specific policy | Additional | A.8.15,A.5.33
15 | Topic-specific policy on the protection of PII | Topic-specific policy | Additional | A.5.34
16 | Topic-specific policy on audit and assessment | Topic-specific policy | Additional | 9.2.2 ¶1,9.2.2 ¶2,9.2.2 a),9.2.2 b)
17 | Topic-specific policy on remote working | Topic-specific policy | Additional | A.6.7
18 | Topic-specific policy on physical and environmental security | Topic-specific policy | Additional | A.7.1,A.7.2,A.7.3,A.7.4,A.7.5,A.7.6,A.7.8,A.7.9,A.7.12
19 | Topic-specific policy on removable storage media | Topic-specific policy | Additional | A.7.10
20 | Topic-specific policy on equipment maintenance | Topic-specific policy | Additional | A.7.13
21 | Procedures for handling information | Procedure | Additional | A.5.10
22 | Procedures for termination or change of employment | Procedure | Additional | A.5.11
23 | Procedures for information labelling | Procedure | Additional | A.5.13
24 | Procedure for authentication information allocation and management | Procedure | Additional | A.5.17
25 | Procedure for access rights review | Procedure | Additional | A.5.18
26 | Procedure for provisioning and revocation of access rights | Procedure | Additional | A.5.18
27 | Procedure for information security incident management | Procedure | Additional | A.5.24
28 | Procedures for intellectual property rights compliance | Procedure | Additional | A.5.32
29 | Procedures for the protection of PII | Procedure | Additional | A.5.34
30 | Operating procedures for information processing facilities | Procedure | Additional | A.5.37
31 | Procedures for personnel screening | Procedure | Additional | A.6.1
32 | Procedures for disciplinary actions | Procedure | Additional | A.6.4
33 | Procedures for reporting information security events | Procedure | Additional | A.6.8
34 | Procedures for authenticating and logging visitors | Procedure | Additional | A.7.2
35 | Procedures for monitoring physical premises | Procedure | Additional | A.7.4
36 | Procedures for working in secure areas | Procedure | Additional | A.7.6
37 | Procedures for secure reuse or disposal of removable storage media | Procedure | Additional | A.7.10,A.7.10
38 | Procedures for equipment maintenance | Procedure | Additional | A.7.13
39 | Procedures for decommissioning of equipment | Procedure | Additional | A.7.14
40 | Procedures for capacity management | Procedure | Additional | A.8.6
41 | Procedure for technical vulnerability management | Procedure | Additional | A.8.8
42 | Procedures for configuration management | Procedure | Additional | A.8.9
43 | Procedures for information deletion | Procedure | Additional | A.8.10
44 | Procedures for monitoring | Procedure | Additional | A.8.16
45 | Procedures for software installation | Procedure | Additional | A.8.19
46 | Procedures for cryptographic key management | Procedure | Additional | A.8.24
47 | Procedures for change control | Procedure | Additional | A.8.32
48 | Information Security Governance Process | Process | Additional | 4.4 ¶1
49 | Resource Management Process | Process | Additional | 4.4 ¶1,7.1 ¶1
50 | Communication Process | Process | Additional | 4.4 ¶1,7.4 a),7.4 b),7.4 c),7.4 d)
51 | Performance Evaluation Process | Process | Additional | 4.4 ¶1
52 | ISMS Change Management Process | Process | Additional | 4.4 ¶1
53 | Control Implementation Process | Process | Additional | 4.4 ¶1
54 | Management Review Process | Process | Additional | 4.4 ¶1
55 | Internal Audit Process | Process | Additional | 4.4 ¶1
56 | Security Awareness and Training Process | Process | Additional | 4.4 ¶1
57 | ISMS Improvement process | Process | Additional | 4.4 ¶1
58 | Context Analysis Process | Process | Additional | 4.4 ¶1
59 | Customer Relationship Management Process | Process | Additional | 4.4 ¶1
60 | Security Policy Management Process | Process | Additional | 4.4 ¶1,A.5.1,7.5.1 a),7.5.1 b),7.5.2 a),7.5.2 b),7.5.2 c),7.5.3 a),7.5.3 b),7.5.3 c),7.5.3 d),7.5.3 e),7.5.3 f),7.5.3 ¶1
61 | Records Control Process | Process | Additional | A.5.33
62 | Supplier management process | Process | Additional | A.5.19
63 | Information security incident management process | Process | Additional
64 | Risk Assessment Process | Process | Mandatory | 4.4 ¶1,6.1.2 b),6.1.2 c) 1),6.1.2 c) 2),6.1.2 d) 1),6.1.2 d) 2),6.1.2 d) 3),6.1.2 e) 1),6.1.2 e) 2),6.1.2 ¶1
65 | Risk Treatment Process | Process | Mandatory | 4.4 ¶1,6.1.3 a),6.1.3 b),6.1.3 c),6.1.3 d),6.1.3 e),6.1.3 f),6.1.3 ¶1
66 | Project Charter | Record | Additional
67 | Business Case | Record | Additional
68 | Gap analysis report | Record | Additional
69 | External and internal Issues | Record | Additional | 4.1 ¶1,4.1 ¶1
70 | Requirements of interested parties | Record | Additional | 4.2 c),A.5.31,4.2 b)
71 | Scope of the ISMS | Record | Mandatory | 4.3 ¶2
72 | Risk Acceptance Criteria | Record | Mandatory | 6.1.2 a) 1)
73 | Risk Assessment Criteria | Record | Mandatory | 6.1.2 a) 2)
74 | Statement of Applicability (SoA) | Record | Mandatory | 8.3 ¶1
75 | Risk Treatment Plan | Record | Mandatory | 8.3 ¶2
76 | Information security objectives | Record | Mandatory | 6.2 ¶1,6.2 a),6.2 b),6.2 c),6.2 d),6.2 e),6.2 f),6.2 g),6.2 ¶2,6.2 h),6.2 i),6.2 j),6.2 k),6.2 l)
77 | Evidence of competence | Record | Mandatory | 7.2 d),A.6.3
78 | Communication Plan | Record | Additional
79 | Carrying out of processes as planned | Record | Mandatory | 8.1 ¶1,8.1 ¶2,8.1 ¶3
80 | Results of information security risk assessments | Record | Mandatory | 8.2 ¶2,A.7.5,A.7.8
81 | Results of the risk treatment process | Record | Mandatory | 8.3 ¶2
82 | Results of monitoring and measurement | Record | Mandatory | 9.1 ¶1
83 | Audit Programme | Record | Mandatory | 9.2.2 ¶3
84 | Audit Reports | Record | Mandatory | 9.2.2 ¶3,9.2.2 c)
85 | Management Reports | Record | Additional | 9.3.2 a),9.3.2 b),9.3.2 c),9.3.2 d) 1),9.3.2 d) 2),9.3.2 d) 3),9.3.2 d) 4),9.3.2 e),9.3.2 f),9.3.2 g)
86 | Results of management reviews | Record | Mandatory | 9.3.3 ¶1,9.3.3 ¶2
87 | Nature of nonconformities and any subsequent actions taken | Record | Mandatory | 10.2 f),10.2 g)
88 | Results of any corrective action | Record | Mandatory | 10.2 f),10.2 g)
89 | Policy acknowledgement records | Record | Additional | A.5.1
90 | Organizational charts | Record | Additional | 5.3 ¶1,5.3 a),5.3 b)
91 | Role definitions and job descriptions | Record | Additional | A.5.2,A.5.3
92 | Register of relevant authorities | Record | Additional | A.5.5
93 | Threat intelligence | Record | Additional | A.5.7
94 | Project documentation | Record | Additional | A.5.8
95 | Information and asset inventory | Record | Additional | A.5.9,A.7.9
96 | Return of assets records | Record | Additional | A.5.11
97 | Access control rules | Record | Additional | A.5.15
98 | Identity management records | Record | Additional | A.5.17
99 | Authentication information | Record | Additional
100 | Access rights records | Record | Additional | A.5.18
101 | Review of access rights records | Record | Additional | A.5.18
102 | Supplier evaluation and selection records | Record | Additional | A.5.19,A.5.21,A.5.23
103 | Supplier agreements | Record | Additional | A.5.20
104 | Service Level Agreements (SLAs) | Record | Additional | A.5.20
105 | Supplier monitoring and review records | Record | Additional | A.5.22
106 | Information security incident management plans | Record | Additional | A.5.24
107 | Information security incident records | Record | Additional | A.5.25,A.5.26
108 | Evidence related to information security events | Record | Additional | A.5.25,A.5.28
109 | Business Continuity Plan (BCP) | Record | Additional | A.5.29
110 | BCP test records | Record | Additional | A.5.29
111 | Business Impact Analysis (BIA) | Record | Additional | A.5.30
112 | ICT continuity plans | Record | Additional | A.5.30
113 | Legal, statutory, regulatory and contractual requirements relevant to information security | Record | Additional | 4.2 c),A.5.31,4.2 b),A.5.31
114 | Personnel screening records | Record | Additional | A.6.1
115 | Employment contractual agreements | Record | Additional | A.6.2,A.6.5
116 | Information security education and training programme | Record | Additional | 7.2 b),A.6.3
117 | Information security awareness programme | Record | Additional | 7.2 b),7.3 a),7.3 b),7.3 c),A.6.3
118 | Information security awareness, training and education participation records | Record | Additional | 7.2 d),A.6.3
119 | Disciplinary action records | Record | Additional | A.6.4
120 | Non-disclosure agreement templates | Record | Additional | A.6.6
121 | Signed non-disclosure agreements | Record | Additional | A.6.6
122 | Site and floor plans | Record | Additional | A.7.1,A.7.3,A.7.12
123 | Visitor management logs | Record | Additional | A.7.2
124 | Physical access logs | Record | Additional | A.7.2
125 | Surveillance footage | Record | Additional | A.7.4
126 | Equipment inventory | Record | Additional | A.7.8
127 | Media usage logs | Record | Additional | A.7.10
128 | Data erasure and disposal certificates | Record | Additional | A.7.10,A.7.14,A.7.10
129 | Utilities inventory | Record | Additional | A.7.11
130 | Equipment maintenance programme | Record | Additional | A.7.13
131 | Equipment maintenance records | Record | Additional | A.7.13
132 | List of authorized maintenance personnel | Record | Additional
133 | Equipment verification records | Record | Additional
134 | System access logs | Record | Additional
135 | Capacity requirements | Record | Additional | A.8.6
136 | Results of vulnerability assessments or penetration tests | Record | Additional | A.8.8
137 | Standard configuration templates | Record | Additional | A.8.9
138 | Configuration logs | Record | Additional | A.8.9
139 | Results of deletion | Record | Additional | A.8.10
140 | Backup plans | Record | Additional | A.8.13
141 | Results of backup media tests | Record | Additional | A.8.13
142 | Network plans | Record | Additional | A.8.20,A.7.12
143 | List of prohibited websites and domains | Record | Additional | A.8.23

## Project Information
Project information
Project name: | ISO/IEC 27001 Implementation Project
Project lead:
Start date: | 2025-06-01
Finish date | 2027-04-12

## Gantt Chart
ISO/IEC 27001 Implementation Project
Input column
| Calculated column | [8 empty] | 45 | [6 empty] | 46 | [6 empty] | 47 | [6 empty] | 48 | [6 empty] | 49 | [6 empty] | 50 | [6 empty] | 51 | [6 empty] | 52
[9 empty] | 75 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12 | 2026-12-13 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19 | 2026-12-20 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26 | 2026-12-27
ID | Type | Task Name | Assignee | Duration | Start | Finish | % | Reference | Deliverable | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | S | 1. Management Support |  | 31 | 2025-06-01 | 2025-07-11 | 46.77%
2 | T | Purchase ISO/IEC 27001:2022 |  | 1 | 2025-06-01 | 2025-06-01 | 100%
3 | T | Understand business vision and objectives |  | 1 | 2025-06-02 | 2025-06-02 | 100% | 6.2
4 | T | Outline business case |  | 9 | 2025-06-03 | 2025-06-13 | 100%
5 | T | Obtain approval for business case |  | 1 | 2025-06-16 | 2025-06-16 | 50%
6 | T | Develop project charter |  | 10 | 2025-06-17 | 2025-06-30 | 30%
7 | T | Obtain approval for project charter |  | 2 | 2025-07-01 | 2025-07-02 |  | 5.1
8 | T | Assign overall responsibility for the ISMS |  | 1 | 2025-07-03 | 2025-07-03 |  | 5.3
9 | T | Communicate roles, responsibilities and authorities for the ISMS |  | 1 | 2025-07-04 | 2025-07-04 |  | 5.3
10 | T | Establish information secuity governance process |  | 5 | 2025-07-07 | 2025-07-11 |  | 5.1, 4.4, 6.2
11 | M | Management support is obtained |  |  | 2025-07-11 | 2025-07-11
12 | S | 2. Scope of the ISMS |  | 37 | 2025-07-14 | 2025-09-02 | 0%
13 | T | Establish context analysis process |  | 5 | 2025-07-14 | 2025-07-18 |  | 4.4
14 | T | Review external environment |  | 5 | 2025-07-21 | 2025-07-25 |  | 4.1
15 | T | Determine external issues |  | 5 | 2025-07-28 | 2025-08-01 |  | 4.1 | External issues (4.1)
16 | T | Review internal aspects | [5 empty] | 4.1
17 | T | Determine internal issues |  | 5 | 2025-08-04 | 2025-08-08 |  | 4.1 | Internal Issues (4.1)
18 | T | Identify external interested parties |  | 3 | 2025-08-11 | 2025-08-13 |  | 4.2 a)
19 | T | Identify internal interested parties |  | 3 | 2025-08-14 | 2025-08-18 |  | 4.2 a)
20 | T | Identify requirements of interested parties |  | 2 | 2025-08-19 | 2025-08-20 |  | 4.2 b), A.5.31 | Requirements of interested parties (4.2), Legal, statutory, regulatory and contractual requirements (A.5.31)
21 | T | Determine which requirements are addressed through the ISMS |  | 1 | 2025-08-21 | 2025-08-21 |  | 4.2 c)
22 | T | Determine preliminary scope |  | 5 | 2025-08-22 | 2025-08-28 |  | 4.3
23 | T | Determine refined scope |  | 1 | 2025-08-29 | 2025-08-29 |  | 4.3
24 | T | Determine final scope |  | 1 | 2025-09-01 | 2025-09-01 |  | 4.3
25 | T | Obtain approval for final scope |  | 1 | 2025-09-02 | 2025-09-02 |  | 4.3
26 | M | ISMS scope is approved |  |  | 2025-09-02 | 2025-09-02 |  | 4.3 | Scope of the ISMS (4.3)
27 | S | 3. Gap Analysis |  | 23 | 2025-09-03 | 2025-10-03 | 0%
28 | T | Define desired state |  | 5 | 2025-09-03 | 2025-09-09
29 | T | Analyze current state |  | 5 | 2025-09-10 | 2025-09-16
30 | T | Compare current state with desired state |  | 5 | 2025-09-17 | 2025-09-23
31 | T | Identify gaps |  | 3 | 2025-09-24 | 2025-09-26
32 | T | Produce gap analysis report |  | 3 | 2025-09-29 | 2025-10-01
33 | T | Update project plan |  | 2 | 2025-10-02 | 2025-10-03
34 | S | 4. Information Security Policy |  | 21 | 2025-10-06 | 2025-11-03 | 0%
35 | T | Establish policy management process |  | 5 | 2025-10-06 | 2025-10-10 |  | 7.5, 4.4, A.5.1
36 | T | Establish communication process |  | 5 | 2025-10-13 | 2025-10-17 |  | 7.4, 4.4
37 | T | Determine information security objectives |  | 3 | 2025-10-20 | 2025-10-22 |  | 6.2 | Information security objectives (6.2)
38 | T | Develop information security policy |  | 6 | 2025-10-23 | 2025-10-30 |  | 5.2
39 | T | Obtain approval for information security policy |  | 2 | 2025-10-31 | 2025-11-03 |  | 5.2
40 | M | Publish information security policy |  |  | 2025-11-03 | 2025-11-03 |  | 5.2, A.5.1 | Information security policy (5.2, A.5.1.1)
41 | S | 5. Competence Assurance |  | 21 | 2025-11-04 | 2025-12-02 | 0%
42 | T | Establish security awareness and training process |  | 5 | 2025-11-04 | 2025-11-10 |  | 4.4
43 | T | Identify roles affecting information security |  | 2 | 2025-11-11 | 2025-11-12 |  | 7.2, A.6.3
44 | T | Determine competence and awareness requirements |  | 2 | 2025-11-13 | 2025-11-14 |  | 7.2, A.6.3
45 | T | Assess current competence and awareness levels |  | 2 | 2025-11-17 | 2025-11-18 |  | 7.2, 7.3
46 | T | Plan IS education and training programme |  | 2 | 2025-11-19 | 2025-11-20 |  | 7.2, 7.3 | Information security education and training programme
47 | T | Plan IS awareness programme |  | 2 | 2025-11-21 | 2025-11-24 |  | 7.3 | Information security awareness programme
48 | T | Conduct IS training and awareness measures |  | 2 | 2025-11-25 | 2025-11-26 |  | 7.2, 7.3, A.6.3
49 | T | Document IS training and awareness results |  | 1 | 2025-11-27 | 2025-11-27 |  | 7.2, 7.3, A.6.3 | Evidence of competence (7.2), IS awareness, training, education participation records
50 | T | Evaluate programme effectiveness |  | 2 | 2025-11-28 | 2025-12-01 |  | 7.2, A.6.3
51 | T | Plan for recruitment or outsourcing |  | 1 | 2025-12-02 | 2025-12-02 |  | 7.2
52 | S | 6. Inventory of Assets |  | 32 | 2025-12-03 | 2026-01-15 | 0%
53 | T | Establish topic-specific policy on asset and configuration management |  | 1 | 2025-12-03 | 2025-12-03 |  | A.5.9
54 | T | Publish topic-specific policy on asset and configuration management |  | 1 | 2025-12-04 | 2025-12-04 |  |  | Topic-specific policy on asset and configuration management
55 | T | Identify primary assets |  | 5 | 2025-12-05 | 2025-12-11 |  | A.5.9
56 | T | Identify supporting assets |  | 5 | 2025-12-12 | 2025-12-18 |  | A.5.9
57 | T | Dpcument and map primary and supporting assets. |  | 5 | 2025-12-19 | 2025-12-25 |  | A.5.9
58 | T | Identify and assign asset owners |  | 2 | 2025-12-26 | 2025-12-29 |  | A.5.9 | Information and asset inventory (A.5.9)
59 | T | Establish topic-specific policy on information classification |  | 5 | 2025-12-30 | 2026-01-05 |  | A.5.12 | Information classification policy (A.5.12)
60 | T | Classify information |  | 2 | 2026-01-06 | 2026-01-07 |  | A.5.12
61 | T | Establish procedures for information labelling |  | 5 | 2026-01-08 | 2026-01-14 |  | A.5.13 | Procedures for information labelling (A.5.13)
62 | T | Label information |  | 1 | 2026-01-15 | 2026-01-15 |  | A.5.13
63 | S | 7. Risk Management Methodology |  | 23 | 2026-01-16 | 2026-02-17 | 0%
64 | T | Define information security risk assessment criteria |  | 3 | 2026-01-16 | 2026-01-20 |  | 6.1.2 a)
65 | T | Define information security risk acceptance criteria |  | 3 | 2026-01-21 | 2026-01-23 |  | 6.1.2 a)
66 | T | Obtain approval for information security risk acceptance criteria |  | 1 | 2026-01-26 | 2026-01-26 |  | 6.1.2 a) | Risk assessment criteria, risk acceptance criteria
67 | T | Establish information security risk assessment process |  | 5 | 2026-01-27 | 2026-02-02 |  | 6.1.2, 4.4 | Information security risk assessment process (6.1.2)
68 | T | Establish information security risk treatment process |  | 5 | 2026-02-03 | 2026-02-09 |  | 6.1.3, 4.4 | Information security risk treatment process (6.1.3)
69 | T | Establish topic-specific policy on risk management |  | 5 | 2026-02-10 | 2026-02-16 |  | 6.1
70 | T | Publish topic-specific policy on risk management |  | 1 | 2026-02-17 | 2026-02-17 |  | 4.4 | Topic-specific policy on risk management
71 | S | 8. Information Security Risk Assessment |  | 35 | 2026-02-18 | 2026-04-07 | 0%
72 | S | Risk identification |  | 18 | 2026-02-18 | 2026-03-13 | 0%
73 | T | Identify threats |  | 2 | 2026-02-18 | 2026-02-19 |  | 8.2
74 | T | Identify existing controls |  | 5 | 2026-02-20 | 2026-02-26 |  | 8.2
75 | T | Identify vulnerabilities |  | 5 | 2026-02-27 | 2026-03-05 |  | 8.2
76 | T | Identify consequences (impact) |  | 3 | 2026-03-06 | 2026-03-10 |  | 8.2
77 | T | Identify risk owners |  | 3 | 2026-03-11 | 2026-03-13 |  | 8.2
78 | S | Risk analysis |  | 10 | 2026-03-16 | 2026-03-27 | 0%
79 | T | Assess consequences (impact) |  | 3 | 2026-03-16 | 2026-03-18 |  | 8.2
80 | T | Assess likelihood |  | 3 | 2026-03-19 | 2026-03-23 |  | 8.2
81 | T | Determine risk level |  | 4 | 2026-03-24 | 2026-03-27 |  | 8.2
82 | S | Risk evaluation |  | 7 | 2026-03-30 | 2026-04-07 | 0%
83 | T | Evaluate risks |  | 5 | 2026-03-30 | 2026-04-03 |  | 8.2
84 | T | Document results of risk assessments |  | 2 | 2026-04-06 | 2026-04-07 |  | 8.2
85 | M | Risk assessment is completed |  |  | 2026-04-07 | 2026-04-07 |  | 8.2 | Results of information security risk assessments (8.2)
86 | S | 9. Information Security Risk Treatment |  | 153 | 2026-04-08 | 2026-11-06 | 0%
87 | S | Develop Risk Treatment Plan |  | 31 | 2026-04-08 | 2026-05-20 |  | 8.3
88 | T | Establish resource management process |  | 5 | 2026-04-08 | 2026-04-14 |  | 7.1, 4.4
89 | T | Select risk treatment options |  | 5 | 2026-04-15 | 2026-04-21 |  | 8.3
90 | T | Determine controls |  | 5 | 2026-04-22 | 2026-04-28 |  | 8.3
91 | T | Produce Statement of Applicability (SoA) |  | 1 | 2026-04-29 | 2026-04-29 |  | 8.3 | Statement of Applicability (SoA) (6.1.3)
92 | T | Formulate risk treatment plan |  | 10 | 2026-04-30 | 2026-05-13 |  | 8.3
93 | T | Obtain approval for risk treatment plan |  | 5 | 2026-05-14 | 2026-05-20 |  | 8.3 | Risk treatment plan (8.3)
94 | M | Risk treatment plan is approved |  |  | 2026-05-20 | 2026-05-20 |  | 8.3
95 | S | Implement Risk Treatment Plan |  | 32 | 2026-05-21 | 2026-07-03 |  | 8.3
96 | T | Implement risk treatment plan |  | 30 | 2026-05-21 | 2026-07-01 |  | A.5.1 | Information security policy
97 | T | Obtain approval für residual risk |  | 1 | 2026-07-02 | 2026-07-02 |  | 8.3
98 | T | Update Statement of Applicability (SoA) |  | 1 | 2026-07-03 | 2026-07-03 |  | 8.3
99 | M | Risk treatment plan is implemented |  |  | 2026-07-03 | 2026-07-03 |  | 8.3 | Results of information security risk treatment (8.3)
100 | S | ISMS Operations |  | 90 | 2026-07-06 | 2026-11-06
101 | T | Operate ISMS processes |  | 30 | 2026-07-06 | 2026-08-14 |  | 8.1 | Carrying out of processes as planned (8.1)
102 | T | Control ISMS processes |  | 30 | 2026-08-17 | 2026-09-25 |  | 8.1
103 | T | Manage outsourced functions |  | 30 | 2026-09-28 | 2026-11-06 |  | 8.1
104 | S | 10. Performance Evaluation |  | 63 | 2026-11-09 | 2027-02-03 | 0%
105 | S | Monitoring |  | 22 | 2026-11-09 | 2026-12-08 | 0%
106 | T | Establish performance evaluation process |  | 5 | 2026-11-09 | 2026-11-13 |  | 4.4
107 | T | Identify information needs |  | 5 | 2026-11-16 | 2026-11-20 |  | 9.1
108 | T | Create and maintain measures |  | 5 | 2026-11-23 | 2026-11-27 |  | 9.1
109 | T | Monitor and measure |  | 2 | 2026-11-30 | 2026-12-01 |  | 9.1
110 | T | Analyse results |  | 1 | 2026-12-02 | 2026-12-02 |  | 9.1
111 | T | Evaluate information security performance |  | 1 | 2026-12-03 | 2026-12-03 |  | 9.1
112 | T | Evaluate ISMS effectiveness |  | 1 | 2026-12-04 | 2026-12-04 |  | 9.1
113 | T | Document results |  | 2 | 2026-12-07 | 2026-12-08 |  | 9.1 | Results of monitoring and measurement (9.1)
114 | S | Internal audit |  | 33 | 2026-12-09 | 2027-01-22 | 0%
115 | T | Establish a topic-specific policy on audit and assessment |  | 5 | 2026-12-09 | 2026-12-15
116 | T | Publish a topic-specific policy on audit and assessment |  | 1 | 2026-12-16 | 2026-12-16 |  |  | Topic-specific policy on audit and assessment
117 | T | Establish internal audit process |  | 5 | 2026-12-17 | 2026-12-23 |  | 4.4
118 | T | Establish audit programme objectives |  | 3 | 2026-12-24 | 2026-12-28 |  | 9.2
119 | T | Determine audit programme risks and opportunities |  | 2 | 2026-12-29 | 2026-12-30 |  | 9.2
120 | T | Evaluate audit programme risks and opportunities |  | 2 | 2026-12-31 | 2027-01-01 |  | 9.2
121 | T | Establish audit programme |  | 2 | 2027-01-04 | 2027-01-05 |  | 9.2 | Audit programme (9.2)
122 | T | Implement audit programme |  | 5 | 2027-01-06 | 2027-01-12 |  | 9.2
123 | T | Conduct internal audits |  | 5 | 2027-01-13 | 2027-01-19 |  | 9.2, A.5.35, A.8.34
124 | T | Report audit results |  | 3 | 2027-01-20 | 2027-01-22 |  | 9.2 | Audit results (9.2)
125 | S | Management review |  | 8 | 2027-01-25 | 2027-02-03 | 0%
126 | T | Establish management review process |  | 1 | 2027-01-25 | 2027-01-25 |  | 9.3
127 | T | Prepare management reports |  | 5 | 2027-01-26 | 2027-02-01 |  | 9.3 | Management reports (9.3)
128 | T | Review management reports of the performance of the ISMS |  | 1 | 2027-02-02 | 2027-02-02 |  | 9.3
129 | T | Document and communicate results of management review |  | 1 | 2027-02-03 | 2027-02-03 |  | 9.3 | Results of management reviews (9.3)
130 | S | 11. Improvement |  | 25 | 2027-02-04 | 2027-03-10 | 0%
131 | T | Establish ISMS improvement process |  | 2 | 2027-02-04 | 2027-02-05 |  | 4.4
132 | T | Establish ISMS change management process |  | 2 | 2027-02-08 | 2027-02-09 |  | 4.4
133 | T | Identify nonconformities |  | 2 | 2027-02-10 | 2027-02-11 |  | 10.2
134 | T | Review nonconformities |  | 2 | 2027-02-12 | 2027-02-15 |  | 10.2 | Nature of the nonconformities and any subsequent actions taken (10.2 f))
135 | T | Perform root cause analysis |  | 2 | 2027-02-16 | 2027-02-17 |  | 10.2
136 | T | Determine corrective actions |  | 3 | 2027-02-18 | 2027-02-22 |  | 10.2
137 | T | Plan corrective actions |  | 2 | 2027-02-23 | 2027-02-24 |  | 10.2
138 | T | Implement corrective actions |  | 5 | 2027-02-25 | 2027-03-03 |  | 10.2
139 | T | Assess corrective actions |  | 3 | 2027-03-04 | 2027-03-08 |  | 10.2
140 | T | Document nonconformities |  | 2 | 2027-03-09 | 2027-03-10 |  | 10.2 | Results of any corrective action (10.2 g))
141 | M | ISMS is compliant |  |  | 2027-03-10 | 2027-03-10 |  | 10.2
142 | S | 12. Certification audit |  | 23 | 2027-03-11 | 2027-04-12 | 0%
143 | T | Contact certfication bodies |  | 1 | 2027-03-11 | 2027-03-11
144 | T | Request proposals |  | 5 | 2027-03-12 | 2027-03-18
145 | T | Review proposals |  | 1 | 2027-03-19 | 2027-03-19
146 | T | Select certification body |  | 1 | 2027-03-22 | 2027-03-22
147 | T | Sign engagement letter |  | 1 | 2027-03-23 | 2027-03-23
148 | T | Schedule stage 1 audit |  | 1 | 2027-03-24 | 2027-03-24
149 | T | Undergo stage 1 audit |  | 5 | 2027-03-25 | 2027-03-31
150 | T | Schedule stage 2 audit |  | 1 | 2027-04-01 | 2027-04-01
151 | T | Undergo stage 2 audit |  | 5 | 2027-04-02 | 2027-04-08
152 | T | Submit corrective action plan |  | 2 | 2027-04-09 | 2027-04-12
153 | M | ISMS is certified |  |  | 2027-04-12 | 2027-04-12 | 0% |  | ISO/IEC 27001 certificate